SmartStudy – Student Learning Management Platform Project Charter

- Project Information

| Project Name: | SmartStudy – Student Learning Management Platform Project Charter | PlanView Number: |  |
| --- | --- | --- | --- |
| Project Sponsor: | WUNU | Project Size: | Medium (Software Development Project) |
| Project Director: |  | Project Start Date: | 25.02.2026 |
| Project Manager: | Anastasiia | Project End Date: |  |

- Project Leads

| Lead Name | Division | Unit |
| --- | --- | --- |
| Anastasiia | IT Department | Project Management |
| Lead Developer | Software Development | Backend Team |
| UI/UX Designer | Design Department | Frontend Team |
| QA Lead | Quality Assurance | Testing Team |

- Project Statement

| Project Area | Description |
| --- | --- |
| Background: | Educational institutions require a centralized digital platform to manage courses, assignments, grades, communication, and learning materials. Current systems are fragmented and lack integration. SmartStudy aims to create a unified, user-friendly Learning Management Platform for students and instructors. |
| Project Vision Statement: | SmartStudy will provide a modern, secure, and scalable learning management platform that enhances student engagement, simplifies academic administration, and improves communication between students and instructors. |
| Objective: |  Develop a web-based LMS platform  Enable course management and assignment tracking  Provide grading and performance analytics  Support communication between students and instructors  Ensure secure authentication and data protection |
| Scope: |  |
| Included in scope: |  User registration & authentication  Student & instructor dashboards  Course creation & enrollment  Assignment submission system  Grade management system  Notifications system  Database design & deployment  Testing & deployment |
| Excluded from scope: |  Mobile native application  Integration with external university ERP systems  AI-based tutoring features  Payment systems |
| Impacts: (Organizational & Technical) | Organizational: - Improved communication - Reduced paperwork - Centralized academic management Technical: - Requires cloud hosting environment - Requires secure database infrastructure - Requires ongoing maintenance and updates |
| Dependencies: |  Availability of development team  Server infrastructure readiness  Stakeholder approval at each milestone |
| Assumptions & Constraints: | Assumptions: - Users have internet access - Stakeholders provide timely feedback - Budget approval is secured Constraints: - 4-month development timeline - Limited development team - Fixed academic calendar deadlines |

- High-level Requirements

| Requirement Area | Projected Steps/Comments |
| --- | --- |
| Authentication System | Secure login, password encryption |
| Database | PostgreSQL database implementation |
| Backend Development | REST API development |
| Frontend Development | Responsive web interface |
| Security | Role-based access control |
| Testing | Unit, integration & system testing |
| Deployment | Cloud hosting setup |

- High-level Deliverables

| Deliverable Type Note: Identify each type as either Business Process or Project Management. | Description |
| --- | --- |
| Business Process | Fully functional LMS platform |
| Business Process | Student & Instructor Dashboards |
| Business Process | Course & Assignment Management Module |
| Project Management | Project Plan |
| Project Management | Risk Management Plan |
| Project Management | Testing Documentation |
| Project Management | Final Project Report |

High-level Timeline

| Milestone | Target Date | Date Achieved |
| --- | --- | --- |
| Requirements Gathering | 10.03.2026 |  |
| System Design | 15.03.2026 |  |
| Backend Development | 7.04.2026 |  |
| Frontend Development | 25.04.2026 |  |
| Testing Phase | 2.05.2026 |  |
| Deployment | 13.06.2026 |  |

- High-level LOE Estimates

| Description of Effort | Estimated # Hours across # Days to Complete | Comments |
| --- | --- | --- |
| Requirements Analysis | 80 hours / 10 days | Stakeholder meetings |
| System Design | 120 hours / 15 days | Architecture design |
| Backend Development | 320 hours / 40 days | API & database |
| Frontend Development | 280 hours / 35 days | UI implementation |
| Testing | 160 hours / 20 days | QA testing |
| Deployment | 40 hours / 5 days | Server setup |
| Total Estimated Effort: ~1000 hours |  |  |

- Project Team

| Project Groups | Division/Units Represented |
| --- | --- |
| Core Group(s): |  Project Manager  Backend Developer  Frontend Developer |
| Subject Matter/Expert(s): | Academic Coordinator |
| Technical Expert(s): |  Database Administrator  Security Specialist |
| Other(s) (please describe): | QA Engineer |

| Steering Committee Member | Division/Units Represented |
| --- | --- |
| Dean | Academic Affairs |
| IT Director | Information Technology |
| Finance Representative | Finance Department |

- Project Status Reports

| Status Report Owner: | Anastasiia – Project Manager |
| --- | --- |

| Status Report Audience: |  |  |
| --- | --- | --- |
| Project Sponsor | Steering Committee | Development Team |

Internal Use Only

Document Change Control

Project Charge Document (M101)

| Version Number | Date | Revision Author | Description |
| --- | --- | --- | --- |
| 1.0 | 9/26/07 | SS-KS | Draft New Template Format (archived original format available via document owner) |
| 1.0 | 10/12/07 | SS-KS | Final draft approved by Project Support. |
| 2.0 | 4/7/08 | SS-KS | Converted to .docx format; file path added to footer. |
| 2.0 | 4/17/08 | SS-KS | Version approved for use. |
| 3.0 | 3/5/09 | SS-KS | Updated to address ITS iterative framework. Version approved by Cathy Curley. |

This document is owned and maintained by MAIS Shared Services, Project Support. Any changes to template format and content must adhere to departmental document management standards.